## Test Plan
Test Plan
Link : | https://docs.google.com/document/d/1BNETQS7E6HEg_KYpJIdBvpnVdv31T9eZEZOflMcZNAo/edit?usp=sharing

## Testcase
Product Name |  | intigriti.com | TC Start Date | 20/10/2025 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Signup | TC End Date | 20/10/2025 | TC Execution End Date | - - |  |  |  |  | PASS | 6
Epic |  |  | Test Case Developed By | Nowrin Jannat | Browser (tested) | Yes |  |  |  |  | FAIL | 3
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 9
#SL | Module | Type of Testing | Features | Test Cases | Expected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Signup | Functional | Usename Field | Verify that username accepts valid input | System accepts a valid username | Found as per expectation | nowrin123 | 1.Go to URL in browser 2.Click on signup button 3.Enter valid username and fillup all field 4.Cick on capcha 5.Click on create account | Click here for prove |  | Passed
2 | Signup | Functional | Usename Field | Verify that username cannot be blank | Error message should be appear username is required | Found as per expectation. | black | 1.Go to URL in browser 2.Click on signup button 3.Blank username and correctly fillup all field 4.Cick on capcha 5.Click on create account | Click here for prove |  | Passed
3 | Signup | Functional | First Name Field | First name verification | If we give spacial character or number should not be signup successful | Found not as per expectation. | @12Nowrin | 1.Go to URL in browser 2.Click on signup button 3. Correctly fillup all field accepts first name field 4.Cick on capcha 5.Click on create account | Click here for prove |  | Failed
4 | Signup | Functional | Last Name Field | Last name verification | If we give spacial character or number should not be registration successful | Found not as per expectation. | @12jannat | 1.Go to URL in browser 2.Click on signup button 3. Correctly fillup all field accepts last name field 4.Cick on capcha 5.Click on create account | Click here for prove |  | Failed
5 | Signup | Functional | Email Field | Verify invalid email format | Error message should be appear email is invalid | Found not as per expectation. | jannatnowhilaijdskeikx@filll.com | 1.Go to URL in browser 2.Click on signup button 3. Correctly fillup all field accepts the email field 4.Cick on capcha 5.Click on create account | Click here for prove |  | Failed
6 | Signup | Functional | Password Field | Password verification | Password should be strong and must be at least 10 character length | Found as per expectation. | 145hg | 1. Go to URL in browser. 2. Click on registration button. 3. Fillup all the field correctly expect password field 4. Click on capcha. 5. Click on the register button. | Click here for prove |  | Passed
7 | Signup | Functional | Confirm Password Field | Confirm password verification | If password and confirm password should be same singup successful | Found as per expectation. | 145hg | 1. Go to URL in browser. 2. Click on registration button. 3. Fillup all the field correctly 4. Click on capcha. 5. Click on the register button. | Click here for prove |  | Passed
8 | Signup | Functional | Terms & Conditions | Verify signup button disabled if Terms not checked | Button should remain disabled | Found as per expectation. | None | 1. Go to URL in browser. 2. Click on registration button. 3. Fillup all the field correctly but don't click check box 4. Click on capcha. 5. Click on the register button. | Click here for prove |  | Passed
9 | Signup | Functional | Create Account Button | Verify successful account creation with valid data | Account created successfully | Found as per expectation. | Valid data for all fields | 1. Go to URL in browser. 2. Click on registration button. 3. Fillup all the field correctly 4. Click on capcha. 5. Click on the register button. | Click here for prove |  | Passed

## Bug Report
Bug Reporting
# SL 01
Issue: First name should not start special character or number.
Reproducing Steps:
1.Go to URL in browser 2.Click on signup button 3.Correctly fillup all field accepts first name field 4.Cick on captcha 5.Click on create account
Env: Production.
Module: Signup
Priority: High
Screenshot: Invalid First Name Error
Expected: If we give spacial character or number should not be signup successful
Responsible QA: Nowrin Jannat
Bug Reporting
# SL 02
Issue: Last name should not start special character or number.
Reproducing Steps:
1.Go to URL in browser 2.Click on signup button 3.Correctly fillup all field accepts last name field 4.Cick on captcha 5.Click on create account
Env: Production.
Module: Signup
Priority: High
Screenshot: Invalid last name error
Expected: If we give spacial character or number should not be registration successful
Responsible QA: Nowrin Jannat
Bug Reporting
# SL 03
Issue: Verify invalid email format
Reproducing Steps:
1.Go to URL in browser 2.Click on signup button 3.Correctly fillup all field accepts email field 4.Cick on captcha 5.Click on create account
Env: Production.
Module: Register
Priority: High
Screenshot: Invalid email address error
Expected: Should not allow registration with invalid email address
Responsible QA: Nowrin Jannat

## MindMap
MindMap for Intigriti.com

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Intigriti.com
Module Name | Signup |  |  |  |  | Total No. | Status
Feature Name | Register Account & Account Login.
Test Case Version | 1 |  |  |  |  | 6 | PASS
Written By | Nowrin Jannat |  |  |  |  | 3 | FAIL
Executed By | Nowrin Jannat |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | xx |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 6 | 3 | 0 | 0 | 9
Grand Total | 6 | 3 | 0 | 0 | 9
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
No | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
No | Usability Testing | Test application from user friendliness perspective.
No | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
No | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
No | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (9/9)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/9)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (6/9)*100 = 66.66%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (3/9)*100 = 0.33%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/9)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A